## Sheet1
Drawing | Description | Plant | Rev | Platform | Tag | Rev1 | Date1 | Desc1 | Dsn1 | Chk1 | Apr1 | Rev2 | Date2 | Desc2 | Dsn2 | Chk2 | Apr2 | Rev3 | Date3 | Desc3 | Dsn3 | Chk3 | Apr3 | Rev4 | Date4 | Desc4 | Dsn4 | Chk4 | Apr4 | Rev5 | Date5 | Desc5 | Dsn5 | Chk5 | Apr5 | Notes | Legend | RefDrawings | StartPage | TitleSize
SLPRAM-TI-G75-PL-0001 | Handling & Lifting Requirements/Lifting Arrangement Drawings | G75 | 00 | COMMON TO ALL PLATFORMS | COMMON TO ALL TAGS | A | 04/30/2020 | ISSUED FOR REVIEW | ES | CS | CS | B | 06/16/2021 | RE-ISSUED FOR REVIEW | ES | CS | CS | 00 | 06/28/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [15 empty] | 5 | 7
SLPRAM-EL-G75-DW-0001 | Power and Control Schematic Diagram for Control Panel | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-EL-G75-DW-0001 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-EL-G75-DW-0017 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-EL-G75-DW-0018 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-EL-G75-DW-0019 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-EL-G75-DW-0020 - MRJN TP-7 |  | 4 | 6
SLPRAM-EL-G74-DW-0002 | Detail Drawing for Motor | G74 | 00 | MRJN 580/589 | G74-16-GM-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - SERIAL NUMBERS - PLATFORM G74-11-GM-7711A/B - SLPRAM-EL-G74-DW-0017 - C2006230667 / C2006230672 - MRJN 510/519 G74-12-GM-7714A/B - SLPRAM-EL-G74-DW-0021 - C2006240972 / C2006240977 - MRJN 521/529,329 G74-16-GM-7718A/B - SLPRAM-EL-G74-DW-0002 - C2006240982 / C2006240987 - MRJN 580/589 G74-19-GM-7723A/B - SLPRAM-EL-G74-DW-0018 - C2006240992 / C2006240997 - MRJN 670/679 G74-20-GM-7725A/B - SLPRAM-EL-G74-DW-0022 - C2006241002 / C2006241007 - MRJN 681/690 G74-22-GM-7732A/B - SLPRAM-EL-G74-DW-0023 - C2006241012 / C2006241017 - MRJN 730/739 G74-23-GM-7730A/B - SLPRAM-EL-G74-DW-0019 - C2006241022 / C2006241027 - MRJN 750/759 G74-27-GM-7738A/B - SLPRAM-EL-G74-DW-0020 - C2006241032 / C2006241037 - MRJN 810/819 G74-28-GM-7741A/B - SLPRAM-EL-G74-DW-0024 - C2006241042 / C2006241047 - MRJN 820/829 |  | 4 | 7
SLPRAM-EL-G75-DW-0002 | Detail Drawing for Motor | G75 | 00 | MRJN TP-11 | G75-44-GM-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - SERIAL NUMBERS - PLATFORM G75-44-GM-0138A/B - SLPRAM-EL-G75-DW-0002 - C2006230637 / C2006230642 - MRJN TP-11 G75-45-GM-0156A/B - SLPRAM-EL-G75-DW-0021 - C2006230647 / C2006230652 - MRJN TP-12 G75-46-GM-0149A/B - SLPRAM-EL-G75-DW-0022 - C2006230657 / C2006230662 - MRJN TP-13 G75-49-GM-0143A/B - SLPRAM-EL-G75-DW-0023 - C2006241052 / C2006241057 - MRJN TP-6 G75-52-GM-0133A/B - SLPRAM-EL-G75-DW-0024 - C2006241062 / C2006241067 - MRJN TP-7 |  | 4 | 7
SLPRAM-EL-G74-DW-0003 | Name Plate Drawing for Motor | G74 | 00 | MRJN 580/589 | G74-16-GM-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-GM-7718A/B - SLPRAM-EL-G74-DW-0003 - MRJN 580/589 G74-11-GM-7711A/B - SLPRAM-EL-G74-DW-0025 - MRJN 510/519 G74-19-GM-7723A/B - SLPRAM-EL-G74-DW-0026 - MRJN 670/679 G74-23-GM-7730A/B - SLPRAM-EL-G74-DW-0027 - MRJN 750/759 G74-27-GM-7738A/B - SLPRAM-EL-G74-DW-0028 - MRJN 810/819 G74-12-GM-7714A/B - SLPRAM-EL-G74-DW-0029 - MRJN 521/529,329 G74-20-GM-7725A/B - SLPRAM-EL-G74-DW-0030 - MRJN 681/690 G74-22-GM-7732A/B - SLPRAM-EL-G74-DW-0031 - MRJN 730/739 G74-28-GM-7741A/B - SLPRAM-EL-G74-DW-0032 - MRJN 820/829 |  | 4 | 7
SLPRAM-EL-G75-DW-0003 | Name Plate Drawing for Motor | G75 | 00 | MRJN TP-11 | G75-44-GM-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GM-0138A/B - SLPRAM-EL-G75-DW-0003 - MRJN TP-11 G75-45-GM-0156A/B - SLPRAM-EL-G75-DW-0025 - MRJN TP-12 G75-46-GM-0149A/B - SLPRAM-EL-G75-DW-0026 - MRJN TP-13 G75-49-GM-0143A/B - SLPRAM-EL-G75-DW-0027 - MRJN TP-6 G75-52-GM-0133A/B - SLPRAM-EL-G75-DW-0028 - MRJN TP-7 |  | 4 | 7
SLPRAM-EL-G74-DW-0004 | Name Plate Drawing for Control Panel | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-EL-G74-DW-0004 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-EL-G74-DW-0033 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-EL-G74-DW-0034 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-EL-G74-DW-0035 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-EL-G74-DW-0036 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-EL-G74-DW-0037 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-EL-G74-DW-0038 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-EL-G74-DW-0039 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-EL-G74-DW-0040 - MRJN 820/829 |  | 4 | 7
SLPRAM-EL-G75-DW-0004 | Name Plate Drawing for Control Panel | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-EL-G75-DW-0004 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-EL-G75-DW-0029 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-EL-G75-DW-0030 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-EL-G75-DW-0031 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-EL-G75-DW-0032 - MRJN TP-7 |  | 4 | 7
SLPRAM-EL-G74-DW-0005 | Electrical/Control Panel Detail Drawings / Front & Back Layout Drawings with BOM | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-EL-G74-DW-0005 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-EL-G74-DW-0041 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-EL-G74-DW-0042 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-EL-G74-DW-0043 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-EL-G74-DW-0044 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-EL-G74-DW-0045 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-EL-G74-DW-0046 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-EL-G74-DW-0047 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-EL-G74-DW-0048 - MRJN 820/829 |  | 4 | 4.5
SLPRAM-EL-G75-DW-0005 | Electrical/Control Panel Detail Drawings / Front & Back Layout Drawings with BOM | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-EL-G75-DW-0005 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-EL-G75-DW-0033 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-EL-G75-DW-0034 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-EL-G75-DW-0035 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-EL-G75-DW-0036 - MRJN TP-7 |  | 4 | 4.5
SLPRAM-EL-G74-DW-0006 | Connection/Interconnection Diagram with Terminal Identification | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-EL-G74-DW-0006 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-EL-G74-DW-0049 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-EL-G74-DW-0050 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-EL-G74-DW-0051 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-EL-G74-DW-0052 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-EL-G74-DW-0053 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-EL-G74-DW-0054 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-EL-G74-DW-0055 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-EL-G74-DW-0056 - MRJN 820/829 |  | 4 | 5.5
SLPRAM-EL-G75-DW-0006 | Connection/Interconnection Diagram with Terminal Identification | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-EL-G75-DW-0006 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-EL-G75-DW-0037 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-EL-G75-DW-0038 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-EL-G75-DW-0039 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-EL-G75-DW-0040 - MRJN TP-7 |  | 4 | 5.5
SLPRAM-EL-G74-DW-0007 | Cable Termination Diagram | G74 | 00 | MRJN 580/589 | G74-16-GM-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-GM-7718A/B - SLPRAM-EL-G74-DW-0007 - MRJN 580/589 G74-11-GM-7711A/B - SLPRAM-EL-G74-DW-0057 - MRJN 510/519 G74-19-GM-7723A/B - SLPRAM-EL-G74-DW-0058 - MRJN 670/679 G74-23-GM-7730A/B - SLPRAM-EL-G74-DW-0059 - MRJN 750/759 G74-27-GM-7738A/B - SLPRAM-EL-G74-DW-0060 - MRJN 810/819 G74-12-GM-7714A/B - SLPRAM-EL-G74-DW-0061 - MRJN 521/529,329 G74-20-GM-7725A/B - SLPRAM-EL-G74-DW-0062 - MRJN 681/690 G74-22-GM-7732A/B - SLPRAM-EL-G74-DW-0063 - MRJN 730/739 G74-28-GM-7741A/B - SLPRAM-EL-G74-DW-0064 - MRJN 820/829 |  | 4 | 7
SLPRAM-EL-G75-DW-0007 | Cable Termination Diagram | G75 | 00 | MRJN TP-11 | G75-44-GM-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GM-0138A/B - SLPRAM-EL-G75-DW-0007 - MRJN TP-11 G75-45-GM-0156A/B - SLPRAM-EL-G75-DW-0041 - MRJN TP-12 G75-46-GM-0149A/B - SLPRAM-EL-G75-DW-0042 - MRJN TP-13 G75-49-GM-0143A/B - SLPRAM-EL-G75-DW-0043 - MRJN TP-6 G75-52-GM-0133A/B - SLPRAM-EL-G75-DW-0044 - MRJN TP-7 |  | 4 | 7
SLPRAM-EL-G74-DW-0008 | Earthing Connection Detail for Pump Skid | G74 | 00 | MRJN 580/589 | G74-16-GM-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-GM-7718A/B - SLPRAM-EL-G74-DW-0008 - MRJN 580/589 G74-11-GM-7711A/B - SLPRAM-EL-G74-DW-0065 - MRJN 510/519 G74-19-GM-7723A/B - SLPRAM-EL-G74-DW-0066 - MRJN 670/679 G74-23-GM-7730A/B - SLPRAM-EL-G74-DW-0067 - MRJN 750/759 G74-27-GM-7738A/B - SLPRAM-EL-G74-DW-0068 - MRJN 810/819 G74-12-GM-7714A/B - SLPRAM-EL-G74-DW-0069 - MRJN 521/529,329 G74-20-GM-7725A/B - SLPRAM-EL-G74-DW-0070 - MRJN 681/690 G74-22-GM-7732A/B - SLPRAM-EL-G74-DW-0071 - MRJN 730/739 G74-28-GM-7741A/B - SLPRAM-EL-G74-DW-0072 - MRJN 820/829 |  | 4 | 7
SLPRAM-EL-G75-DW-0008 | Earthing Connection Detail for Pump Skid | G75 | 00 | MRJN TP-11 | G75-44-GM-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GM-0138A/B - SLPRAM-EL-G75-DW-0008 - MRJN TP-11 G75-45-GM-0156A/B - SLPRAM-EL-G75-DW-0045 - MRJN TP-12 G75-46-GM-0149A/B - SLPRAM-EL-G75-DW-0046 - MRJN TP-13 G75-49-GM-0143A/B - SLPRAM-EL-G75-DW-0047 - MRJN TP-6 G75-52-GM-0133A/B - SLPRAM-EL-G75-DW-0048 - MRJN TP-7 |  | 4 | 7
SLPRAM-IN-G74-DW-0001 | Cause & Effect Charts | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-IN-G75-DW-0001 | Cause & Effect Charts | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ME-G74-DW-0003 | Coupling Outline Drawing | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-ME-G74-DW-0003 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-ME-G74-DW-0026 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-ME-G74-DW-0027 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-ME-G74-DW-0028 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-ME-G74-DW-0029 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-ME-G74-DW-0030 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-ME-G74-DW-0031 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-ME-G74-DW-0032 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-ME-G74-DW-0033 - MRJN 820/829 |  | 4 | 7
SLPRAM-ME-G75-DW-0003 | Coupling Outline Drawing | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-ME-G75-DW-0003 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-ME-G75-DW-0021 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-ME-G75-DW-0022 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-ME-G75-DW-0023 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-ME-G75-DW-0024 - MRJN TP-7 |  | 4 | 7
SLPRAM-ME-G74-DW-0004 | Pump Cross Sectional Drawing & BOM | G74 | B | MRJN 580/589 | G74-16-G-7718A/B | A | 04/30/2020 | ISSUED FOR REVIEW | ES | CS | CS | B | 06/25/2021 | RE-ISSUED FOR REVIEW | ES | CS | CS | [19 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-11-G-7711A/B - SLPRAM-ME-G74-DW-0034 - MRJN 510/519 G74-12-G-7714A/B - SLPRAM-ME-G74-DW-0038 - MRJN 521/529,329 G74-16-G-7718A/B - SLPRAM-ME-G74-DW-0004 - MRJN 580/589 G74-19-G-7723A/B - SLPRAM-ME-G74-DW-0035 - MRJN 670/679 G74-20-G-7725A/B - SLPRAM-ME-G74-DW-0039 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-ME-G74-DW-0040 - MRJN 730/739 G74-23-G-7730A/B - SLPRAM-ME-G74-DW-0036 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-ME-G74-DW-0037 - MRJN 810/819 G74-28-G-7741A/B - SLPRAM-ME-G74-DW-0041 - MRJN 820/829 |  | 4 | 7
SLPRAM-ME-G75-DW-0004 | Pump Cross Sectional Drawing & BOM | G75 | B | MRJN TP-11 | G75-44-G-0138A/B | A | 04/30/2020 | ISSUED FOR REVIEW | ES | CS | CS | B | 06/25/2021 | RE-ISSUED FOR REVIEW | ES | CS | CS | [19 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. G75-44-G-0138A/B - SLPRAM-ME-G75-DW-0004 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-ME-G75-DW-0025 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-ME-G75-DW-0026 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-ME-G75-DW-0027 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-ME-G75-DW-0028 - MRJN TP-7 |  | 4 | 7
SLPRAM-ME-G74-DW-0005 | Detail Drawing for Gear Reducer | G74 | 00 | MRJN 580/589 | G74-16-GG-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | AVAILABLE SPARES PART NUMBER - DESCRIPTION GBX16248-1 - K10 Gearhead Kit GBX16248-2 - NEMA Motor adaptor 324/326TC GBX16248-3 - Primary gear set 135 crs 0.8/2 GBX16248-4 - K10 output shaft GBX16248-5 - Breather extension pipe GBX16248-6 - Output flange SEE SPDP FOR FULL DETAILS | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-GG-7718A/B - SLPRAM-ME-G74-DW-0005 - MRJN 580/589 G74-11-GG-7711A/B - SLPRAM-ME-G74-DW-0042 - MRJN 510/519 G74-19-GG-7723A/B - SLPRAM-ME-G74-DW-0043 - MRJN 670/679 G74-23-GG-7730A/B - SLPRAM-ME-G74-DW-0044 - MRJN 750/759 G74-27-GG-7738A/B - SLPRAM-ME-G74-DW-0045 - MRJN 810/819 G74-12-GG-7714A/B - SLPRAM-ME-G74-DW-0046 - MRJN 521/529,329 G74-20-GG-7725A/B - SLPRAM-ME-G74-DW-0047 - MRJN 681/690 G74-22-GG-7732A/B - SLPRAM-ME-G74-DW-0048 - MRJN 730/739 G74-28-GG-7741A/B - SLPRAM-ME-G74-DW-0049 - MRJN 820/829 |  | 4 | 7
SLPRAM-ME-G75-DW-0005 | Detail Drawing for Gear Reducer | G75 | 00 | MRJN TP-11 | G75-44-GG-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | AVAILABLE SPARES PART NUMBER - DESCRIPTION GBX16248-1 - K10 Gearhead Kit GBX16248-2 - NEMA Motor adaptor 324/326TC GBX16248-3 - Primary gear set 135 crs 0.8/2 GBX16248-4 - K10 output shaft GBX16248-5 - Breather extension pipe GBX16248-6 - Output flange SEE SPDP FOR FULL DETAILS | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GG-0138A/B - SLPRAM-ME-G75-DW-0005 - MRJN TP-11 G75-45-GG-0156A/B - SLPRAM-ME-G75-DW-0029 - MRJN TP-12 G75-46-GG-0149A/B - SLPRAM-ME-G75-DW-0030 - MRJN TP-13 G75-49-GG-0143A/B - SLPRAM-ME-G75-DW-0031 - MRJN TP-6 G75-52-GG-0133A/B - SLPRAM-ME-G75-DW-0032 - MRJN TP-7 |  | 4 | 7
SLPRAM-ME-G74-DW-0006 | Detail Drawing for Pulsation Damper - Suction | G74 | 00 | MRJN 580/589 | G74-16-GD-7751A/C | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NOTE: - PRECHARGE PRESSURE TO BE SET AT 80% OF OPERATING PRESSURE. THIS VALUE TO BE ADJUSTED BASED ON THE SITE OPERATING PRESSURE. - NACE MR0175 AND ISO 15156-1/2/3 COMPLIANCE. - RF FLANGE FACE FINISH IS CONCENTRIC SERRATED WITH ROUGHNESS 125-250 MICRO INCH AARH. - THREADING SERIES IS UNC-8 AS PER ASME B1.1. - DAMPER VOLUME 0.5L | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-11-GD-7752A/C - SLPRAM-ME-G74-DW-0050 - MRJN 510/519 G74-12-GD-7757A/C - SLPRAM-ME-G74-DW-0054 - MRJN 521/529,329 G74-16-GD-7751A/C - SLPRAM-ME-G74-DW-0006 - MRJN 580/589 G74-19-GD-7745A/C - SLPRAM-ME-G74-DW-0051 - MRJN 670/679 G74-20-GD-7749A/C - SLPRAM-ME-G74-DW-0055 - MRJN 681/690 G74-22-GD-7748A/C - SLPRAM-ME-G74-DW-0056 - MRJN 730/739 G74-23-GD-7759A/C - SLPRAM-ME-G74-DW-0052 - MRJN 750/759 G74-27-GD-7761A/C - SLPRAM-ME-G74-DW-0053 - MRJN 810/819 G74-28-GD-7755A/C - SLPRAM-ME-G74-DW-0057 - MRJN 820/829 | Applicable damper tag numbers: G74-16-GD-7751A/C G74-11-GD-7752A/C G74-19-GD-7745A/C G74-23-GD-7759A/C G74-27-GD-7761A/C G74-12-GD-7757A/C G74-20-GD-7749A/C G74-22-GD-7748A/C G74-28-GD-7755A/C | 4 | 7
SLPRAM-ME-G75-DW-0006 | Detail Drawing for Pulsation Damper - Suction | G75 | 00 | MRJN TP-11 | G75-44-GD-0172A/C | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NOTE: - PRECHARGE PRESSURE TO BE SET AT 80% OF OPERATING PRESSURE. THIS VALUE TO BE ADJUSTED BASED ON THE SITE OPERATING PRESSURE. - NACE MR0175 AND ISO 15156-1/2/3 COMPLIANCE. - RF FLANGE FACE FINISH IS CONCENTRIC SERRATED WITH ROUGHNESS 125-250 MICRO INCH AARH. - THREADING SERIES IS UNC-8 AS PER ASME B1.1. - DAMPER VOLUME 0.5L. | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. G75-44-GD-0172A/C - SLPRAM-ME-G75-DW-0006 - MRJN TP-11 G75-45-GD-0173A/C - SLPRAM-ME-G75-DW-0033 - MRJN TP-12 G75-46-GD-0170A/C - SLPRAM-ME-G75-DW-0034 - MRJN TP-13 G75-49-GD-0175A/C - SLPRAM-ME-G75-DW-0035 - MRJN TP-6 G75-52-GD-0178A/C - SLPRAM-ME-G75-DW-0036 - MRJN TP-7 | Applicable damper tag numbers: G75-44-GD-0172A/C G75-45-GD-0173A/C G75-46-GD-0170A/C G75-49-GD-0175A/C G75-52-GD-0178A/C | 4 | 7
SLPRAM-ME-G74-DW-0007 | Detail Drawing for Pulsation Damper - Discharge | G74 | 00 | MRJN 580/589 | G74-16-GD-7751B/D | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NOTE: - PRECHARGE PRESSURE TO BE SET AT 80% OF OPERATING PRESSURE. THIS VALUE TO BE ADJUSTED BASED ON THE SITE OPERATING PRESSURE. - MINIMUM RTJ GROOVE HARDNESS: 210 BHN. FINISH: 63 MICRO INCH AARH. - NACE MR0175 AND ISO 15156-1/2/3 COMPLIANCE. - THREADING SERIES IS UNC-8 AS PER ASME B1.1. - DAMPER VOLUME 0.5L. - LIFTING EYEBOLTS TO BE PTFE COATED TO 09-SAMSS-107. | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-11-GD-7752B/D - SLPRAM-ME-G74-DW-0058 - MRJN 510/519 G74-12-GD-7757B/D - SLPRAM-ME-G74-DW-0062 - MRJN 521/529,329 G74-16-GD-7751B/D - SLPRAM-ME-G74-DW-0007 - MRJN 580/589 G74-19-GD-7745B/D - SLPRAM-ME-G74-DW-0059 - MRJN 670/679 G74-20-GD-7749B/D - SLPRAM-ME-G74-DW-0063 - MRJN 681/690 G74-22-GD-7748B/D - SLPRAM-ME-G74-DW-0064 - MRJN 730/739 G74-23-GD-7759B/D - SLPRAM-ME-G74-DW-0060 - MRJN 750/759 G74-27-GD-7761B/D - SLPRAM-ME-G74-DW-0061 - MRJN 810/819 G74-28-GD-7755B/D - SLPRAM-ME-G74-DW-0065 - MRJN 820/829 | Applicable damper tag numbers: G74-16-GD-7751B/D G74-11-GD-7752B/D G74-19-GD-7745B/D G74-23-GD-7759B/D G74-27-GD-7761B/D G74-12-GD-7757B/D G74-20-GD-7749B/D G74-22-GD-7748B/D G74-28-GD-7755B/D | 4 | 7
SLPRAM-ME-G75-DW-0007 | Detail Drawing for Pulsation Damper - Discharge | G75 | 00 | MRJN TP-11 | G75-44-GD-0172B/D | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NOTE: - PRECHARGE PRESSURE TO BE SET AT 80% OF OPERATING PRESSURE. THIS VALUE TO BE ADJUSTED BASED ON THE SITE OPERATING PRESSURE. - MINIMUM RTJ GROOVE HARDNESS: 210 BHN. FINISH: 63 MICRO INCH AARH. - NACE MR0175 AND ISO 15156-1/2/3 COMPLIANCE. - THREADING SERIES IS UNC-8 AS PER ASME B1.1. - DAMPER VOLUME 0.5L. - LIFTING EYEBOLTS TO BE PTFE COATED TO 09-SAMSS-107. | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GD-0172B/D - SLPRAM-ME-G75-DW-0007 - MRJN TP-11 G75-45-GD-0173B/D - SLPRAM-ME-G75-DW-0037 - MRJN TP-12 G75-46-GD-0170B/D - SLPRAM-ME-G75-DW-0038 - MRJN TP-13 G75-49-GD-0175B/D - SLPRAM-ME-G75-DW-0039 - MRJN TP-6 G75-52-GD-0178B/D - SLPRAM-ME-G75-DW-0040 - MRJN TP-7 | Applicable damper tag numbers: G75-44-GD-0172B/D G75-45-GD-0173B/D G75-46-GD-0170B/D G75-49-GD-0175B/D G75-52-GD-0178B/D | 4 | 7
SLPRAM-ME-G74-DW-0008 | Name Plate Drawing for Pumps | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 06/16/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-ME-G74-DW-0008 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-ME-G74-DW-0066 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-ME-G74-DW-0067 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-ME-G74-DW-0068 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-ME-G74-DW-0069 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-ME-G74-DW-0070 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-ME-G74-DW-0071 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-ME-G74-DW-0072 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-ME-G74-DW-0073 - MRJN 820/829 |  | 4 | 7
SLPRAM-ME-G75-DW-0008 | Name Plate Drawing for Pumps | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 06/16/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-ME-G75-DW-0008 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-ME-G75-DW-0041 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-ME-G75-DW-0042 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-ME-G75-DW-0043 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-ME-G75-DW-0044 - MRJN TP-7 |  | 4 | 7
SLPRAM-ME-G74-DW-0009 | Name Plate Drawing for Gear Reducer | G74 | 00 | MRJN 580/589 | G74-16-GG-7718A/B | 00 | 06/23/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NAMEPLATES TO BE AFFIXED USING ST/ST FASTENERS | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-GG-7718A/B - SLPRAM-ME-G74-DW-0009 - MRJN 580/589 G74-11-GG-7711A/B - SLPRAM-ME-G74-DW-0074 - MRJN 510/519 G74-19-GG-7723A/B - SLPRAM-ME-G74-DW-0075 - MRJN 670/679 G74-23-GG-7730A/B - SLPRAM-ME-G74-DW-0076 - MRJN 750/759 G74-27-GG-7738A/B - SLPRAM-ME-G74-DW-0077 - MRJN 810/819 G74-12-GG-7714A/B - SLPRAM-ME-G74-DW-0078 - MRJN 521/529,329 G74-20-GG-7725A/B - SLPRAM-ME-G74-DW-0079 - MRJN 681/690 G74-22-GG-7732A/B - SLPRAM-ME-G74-DW-0080 - MRJN 730/739 G74-28-GG-7741A/B - SLPRAM-ME-G74-DW-0081 - MRJN 820/829 |  | 4 | 7
SLPRAM-ME-G75-DW-0009 | Name Plate Drawing for Gear Reducer | G75 | 00 | MRJN TP-11 | G75-44-GG-0138A/B | 00 | 06/23/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | NAMEPLATES TO BE AFFIXED USING ST/ST FASTENERS | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-GG-0138A/B - SLPRAM-ME-G75-DW-0009 - MRJN TP-11 G75-45-GG-0156A/B - SLPRAM-ME-G75-DW-0045 - MRJN TP-12 G75-46-GG-0149A/B - SLPRAM-ME-G75-DW-0046 - MRJN TP-13 G75-49-GG-0143A/B - SLPRAM-ME-G75-DW-0047 - MRJN TP-6 G75-52-GG-0133A/B - SLPRAM-ME-G75-DW-0048 - MRJN TP-7 |  | 4 | 7
SLPRAM-PS-G74-DW-0001 | Piping & Instrument Diagrams | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | 1. DAMPENERS TO BE SUPPLIED LOOSE AND MOUNTED IN CUSTOMER PIPEWORK. 2. PACKING RECOVERY IS ROUTED DIRECTLY BACK TO PUMP SUCTION CHAMBER. | (SG) DENOTES OIL SIGHT GLASS -¦¦- DENOTES PROCESS CONNECTION | SLPRAM-ME-G74-DW-0001 General Arrangement Drawing for Slops Pump A SLPRAM-ME-G74-DW-0002 General Arrangement Drawing for Slops Pump B SLPRAM-EL-G74-DW-0005 Electrical/Control Panel Detail Drawings Front & Back Layout Drawings with BOM SLPRAM-ME-G74-DW-0004 Pump Cross Sectional Drawing & BOM SLPRAM-ME-G74-DW-0006 Detail Drawing for Pulsation Damper - Suction SLPRAM-ME-G74-DW-0007 Detail Drawing for Pulsation Damper - Discharge | 4 | 7
SLPRAM-PS-G75-DW-0001 | Piping & Instrument Diagrams | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [24 empty] | 1. DAMPENERS TO BE SUPPLIED LOOSE AND MOUNTED IN CUSTOMER PIPEWORK. 2. PACKING RECOVERY IS ROUTED DIRECTLY BACK TO PUMP SUCTION CHAMBER. | (SG) DENOTES OIL SIGHT GLASS -¦¦- DENOTES PROCESS CONNECTION | SLPRAM-ME-G75-DW-0001 General Arrangement Drawing for Slops Pump SLPRAM-EL-G75-DW-0005 Electrical/Control Panel Detail Drawings Front & Back Layout Drawings with BOM SLPRAM-ME-G75-DW-0004 Pump Cross Sectional Drawing & BOM SLPRAM-ME-G75-DW-0006 Detail Drawing for Pulsation Damper - Suction SLPRAM-ME-G75-DW-0007 Detail Drawing for Pulsation Damper - Discharge | 4 | 7
SLPRAM-ST-G74-DW-0001 | Skid Base Structural Drawing (with BOM) | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-ST-G74-DW-0001 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-ST-G74-DW-0002 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-ST-G74-DW-0003 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-ST-G74-DW-0004 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-ST-G74-DW-0005 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-ST-G74-DW-0006 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-ST-G74-DW-0007 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-ST-G74-DW-0008 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-ST-G74-DW-0009 - MRJN 820/829 |  | 4 | 7
SLPRAM-ST-G75-DW-0001 | Skid Base Structural Drawing (with BOM) | G75 | 00 | MRJN TP-11 | G75-44-G-0138A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G75-44-G-0138A/B - SLPRAM-ST-G75-DW-0001 - MRJN TP-11 G75-45-G-0156A/B - SLPRAM-ST-G75-DW-0003 - MRJN TP-12 G75-46-G-0149A/B - SLPRAM-ST-G75-DW-0004 - MRJN TP-13 G75-49-G-0143A/B - SLPRAM-ST-G75-DW-0005 - MRJN TP-6 G75-52-G-0133A/B - SLPRAM-ST-G75-DW-0006 - MRJN TP-7 |  | 4 | 7
SLPRAM-EL-G74-DW-0001 | Power and Control Schematic Diagram for Control Panel | G74 | 00 | MRJN 580/589 | G74-16-G-7718A/B | 00 | 05/17/2021 | ISSUED FOR CONSTRUCTION | ES | CS | CS | [25 empty] | This document is applicable for below listed TAG NUMBERS. Unique documents as indicated shall be submitted as part of NMR-603. ITEM TAG NUMBER - DOCUMENT NUMBER - PLATFORM G74-16-G-7718A/B - SLPRAM-EL-G74-DW-0001 - MRJN 580/589 G74-11-G-7711A/B - SLPRAM-EL-G74-DW-0009 - MRJN 510/519 G74-19-G-7723A/B - SLPRAM-EL-G74-DW-0010 - MRJN 670/679 G74-23-G-7730A/B - SLPRAM-EL-G74-DW-0011 - MRJN 750/759 G74-27-G-7738A/B - SLPRAM-EL-G74-DW-0012 - MRJN 810/819 G74-12-G-7714A/B - SLPRAM-EL-G74-DW-0013 - MRJN 521/529,329 G74-20-G-7725A/B - SLPRAM-EL-G74-DW-0014 - MRJN 681/690 G74-22-G-7732A/B - SLPRAM-EL-G74-DW-0015 - MRJN 730/739 G74-28-G-7741A/B - SLPRAM-EL-G74-DW-0016 - MRJN 820/829 |  | 4 | 6
SLPRAM-EL-G75-DW-0009 | Power and Control Schematic Diagram for Control Panel | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 09/10/2020 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-EL-G75-DW-0016 | Earthing Connection Detail for Pump Skid | G75 | A | MRJN TP-2A | G75-47-GM-0164A/B | A | 09/09/2020 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-IN-G75-DW-0002 | Cause & Effect Charts | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A |  | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ME-G75-DW-0010 | Coupling Outline Drawing | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A |  | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-EL-G75-DW-0010 | Detail Drawing for Motor | G75 | A | MRJN TP-2A | G75-47-GM-0164A/B | [33 empty] | 4 | 7
SLPRAM-EL-G75-DW-0011 | Name Plate Drawing for Motor | G75 | A | MRJN TP-2A | G75-47-GM-0164A/B | [33 empty] | 4 | 7
SLPRAM-EL-G75-DW-0012 | Name Plate Drawing for Control Panel | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 09/23/2020 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-EL-G75-DW-0013 | Electrical/Control Panel Detail Drawings / Front & Back Layout Drawings with BOM | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 44034 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-EL-G75-DW-0014 | Connection/Interconnection Diagram with Terminal Identification | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 44034 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-EL-G75-DW-0015 | Cable Termination Diagram | G75 | A | MRJN TP-2A | G75-47-GM-0164A/B | A | 44036 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ME-G75-DW-0011 | Pump Cross Sectional Drawing & BOM | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 44054 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ME-G75-DW-0012 | Detail Drawing for Gear Reducer | G75 | A | MRJN TP-2A | G75-47-GG-0164A/B | A | 44084 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ME-G75-DW-0013 | Detail Drawing for Pulsation Damper - Suction | G75 | A | MRJN TP-2A | G75-47-GD-0171A/C | A | 44083 | ISSUED FOR REVIEW | ES | CS | CS | [24 empty] | NOTE: - PRECHARGE PRESSURE TO BE SET AT 80% OF OPERATING PRESSURE. THIS VALUE TO BE ADJUSTED BASED ON THE SITE OPERATING PRESSURE. - NACE MR0175 AND ISO 15156-1/2/3 COMPLIANCE. - RF FLANGE FACE FINISH IS CONCENTRIC SERRATED WITH ROUGHNESS 125-250 MICRO INCH AARH. - THREADING SERIES IS UNC-8 AS PER ASME B1.1. - DAMPER VOLUME 0.5L. |  |  | 4 | 7
SLPRAM-ME-G75-DW-0014 | Detail Drawing for Pulsation Damper - Discharge | G75 | A | MRJN TP-2A | G75-47-GD-0171B/D | [33 empty] | 4 | 7
SLPRAM-ME-G75-DW-0015 | Name Plate Drawing for Pumps | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | [33 empty] | 4 | 7
SLPRAM-ME-G75-DW-0016 | Name Plate Drawing for Gear Reducer | G75 | A | MRJN TP-2A | G75-47-GG-0164A/B | [33 empty] | 4 | 7
SLPRAM-PS-G75-DW-0002 | Piping & Instrument Diagrams | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 44055 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-ST-G75-DW-0002 | Skid Base Structural Drawing (with BOM) | G75 | A | MRJN TP-2A | G75-47-G-0164A/B | A | 44097 | ISSUED FOR REVIEW | ES | CS | CS | [27 empty] | 4 | 7
SLPRAM-TI-G75-PL-0003 | Transport Drawings | G75 | C | VARIOUS | VARIOUS | A | 05/01/2020 | ISSUED FOR REVIEW | ES | CS | CS | B | 09/25/2020 | RE-ISSUED FOR REVIEW | ES | CS | CS | C | 02/12/2021 | RE-ISSUED FOR REVIEW | ES | CS | CS | [12 empty] | PACKING AND SHIPPING METHODS ARE IN COMPLIANCE WITH SAEP-385 TABLE A-2006 |  |  | 4 | 7

## Sheet2
| x | y | f
Drawing | 1282 | 984 | 6.5
Description | 1222 | 928.5 | 7
Plant | 1230 | 985 | 7
Rev | 1404 | 985 | 7
Platform | 1302 | 953 | 7
Tag | 1289.5 | 941.5 | 7
Rev1 | 1233.5 | 671 | 6
Date1 | 1252 | 671 | 6
Desc1 | 1285 | 671 | 6
Dsn1 | 1377.5 | 671 | 6
Chk1 | 1393.5 | 671 | 6
Apr1 | 1409.5 | 671 | 6
Rev2 | 1233.5 | 664 | 6
Date2 | 1252 | 664 | 6
Desc2 | 1285 | 664 | 6
Dsn2 | 1377.5 | 664 | 6
Chk2 | 1393.5 | 664 | 6
Apr2 | 1409.5 | 664 | 6
Rev3 | 1233.5 | 656 | 6
Date3 | 1252 | 656 | 6
Desc3 | 1285 | 656 | 6
Dsn3 | 1377.5 | 656 | 6
Chk3 | 1393.5 | 656 | 6
Apr3 | 1409.5 | 656 | 6
Rev4 | 1233.5 | 649 | 6
Date4 | 1252 | 649 | 6
Desc4 | 1285 | 649 | 6
Dsn4 | 1377.5 | 649 | 6
Chk4 | 1393.5 | 649 | 6
Apr4 | 1409.5 | 649 | 6
Rev5 | 1233.5 | 641.5 | 6
Date5 | 1252 | 641.5 | 6
Desc5 | 1285 | 641.5 | 6
Dsn5 | 1377.5 | 641.5 | 6
Chk5 | 1393.5 | 641.5 | 6
Apr5 | 1409.5 | 641.5 | 6
Notes | 1221 | 40 | 6.5
Legend | 1221 | 190 | 4
RefDrawings | 1221 | 520 | 6.5